## Slide 1: Project Progress Forum II
Team LORT
March 23 2015

## Slide 2: Schedule for remaining tasks
Deadlines:
  Tuesday March 24 -> ½ scenes animated
  Saturday March 28 -> all scenes animated
  Sunday March 29 -> final video compilation

## Slide 3: Gary

## Slide 4: Gary
Completed Tasks:
  Created Eiffel tower model
  Set up max files for each scene
  Created prop models
Outstanding tasks:
  Animate scenes 6, 13, 20-23

## Slide 5: Justin

## Slide 6: Justin
Completed Tasks:
  Create Arc de triomphe and road models
  Creating soundtrack
  Rigging character models
Outstanding tasks:
  Animate scenes at the Arc and the river (scenes 8-12)

## Slide 7: Sam

## Slide 8: Sam
Completed Tasks:
  Creating car, building, and the Louvre models
  Texturing cars, buildings
  Adding hair to models
  Creating template for character bodies
Outstanding tasks:
  Animate bakery scenes (scenes 2-5)

## Slide 9: Sasha

## Slide 10: Sasha
Completed Tasks:
  Creating character models
  Texturing character models
  Texturing some buildings
Outstanding tasks:
  Animate scenes on the highway and at the intersection (scenes 7 and 14-21)